Project overview — social media platform

A full-stack, cloud-native social media platform built from scratch to production. 10 weeks total across 5 phases. You will build 8 microservices, deploy them on EKS, wire up 14 AWS services, and implement the hybrid fan-out feed system that powers platforms like Twitter and Instagram.

10 weeks total 8 microservices 14 AWS services Solo buildable

Full tech stack

Frontend

React 18, TypeScript, TailwindCSS, React Query, Zustand, Vite

Backend

Node.js, Express / Fastify, TypeScript, Prisma ORM

Databases

Aurora PostgreSQL, DynamoDB, ElastiCache (Redis)

Messaging

SQS (fan-out workers), SNS (notifications), Redis Pub/Sub

Infrastructure

Terraform, EKS, Helm, ArgoCD, ECR, VPC

Auth

AWS Cognito, JWT, OAuth2 (Google), API Gateway authorizers

Media

S3, Lambda (resize), MediaConvert, CloudFront CDN

Observability

CloudWatch, X-Ray, Prometheus, Grafana, structured logging

CI/CD

GitHub Actions, CodeBuild, ECR, ArgoCD GitOps

Security

WAF, Secrets Manager, KMS, IRSA, Network Policies

8 microservices you will build

- User service — registration, profiles, follow/unfollow, follower counts, user search

- Post service — create, delete, get posts, hashtag parsing, media attachment

- Feed service — hybrid fan-out assembly, timeline pagination, cache invalidation

- Interaction service — likes, comments, reposts, bookmarks, counters

- Notification service — real-time alerts, email via SES, unread badge counts

- Search service — user search, hashtag search, full-text post search via OpenSearch

- Media service — upload, resize to 4 resolutions, video transcode, CDN URLs

- Analytics service — post impressions, profile visits, follower growth events

That's your complete 10-week plan — click through each phase tab for the full week-by-week breakdown with every task, deliverable, and AWS service involved.

A few things worth highlighting about how this plan is structured:

The first two weeks are entirely infrastructure — no application code. This is the professional way to do it. Most people jump straight to writing features and then spend week 7 trying to figure out Terraform while also debugging their app. Setting up EKS, Aurora, ElastiCache, CI/CD, and ArgoCD first means every week after that is just git push to deploy.

Phase 3 (the feed engine) is where you should expect to spend the most debugging time. The fan-out worker sounds simple but the edge cases are tricky — what happens if a SQS message is processed twice? What if Redis is full? What if the follower list DynamoDB query takes 3 pages? Budget extra time here.

Week 10 is not optional. The demo video and the blog post are what get this project noticed. A GitHub repo with no README and no demo is invisible. Engineers have been hired specifically because a recruiter found their blog post explaining the Twitter fan-out problem.

Use the buttons at the bottom of each phase to get the actual code — I can give you the Terraform, the complete service code, Helm charts, k6 scripts, or whatever you need for any specific week.

Phase 1 — Foundation & infrastructure (weeks 1–2)

Set up everything before writing a single line of application code. AWS account structure, VPC, EKS cluster, databases, CI/CD pipeline, and local development environment. A solid foundation here prevents 80% of later problems.

Weeks 1–2 Infrastructure first Zero app code yet

Week 1

AWS setup, networking & cluster

- Create AWS account, set up IAM admin user, enable MFA, configure AWS CLI and credentials

- Write Terraform for VPC — 3 public subnets, 3 private subnets across 3 AZs, NAT gateway, Internet gateway, route tables

- Provision EKS cluster (v1.29) with Terraform — 2 node groups: general (t3.medium x3) and memory-optimized for Redis workloads

- Install EKS add-ons: AWS Load Balancer Controller, EBS CSI driver, CoreDNS, kube-proxy, VPC CNI

- Set up kubectl, configure kubeconfig, verify cluster connectivity, deploy a test nginx pod

- Create ECR repositories for all 8 microservices and the frontend

- Set up Kubernetes namespaces: dev, staging, production, monitoring

EKSVPCECRIAMTerraform

Working EKS cluster reachable from your machine

Week 2

Databases, secrets, CI/CD pipeline

- Provision Aurora PostgreSQL cluster (Multi-AZ) in private subnets via Terraform. Create separate databases per microservice (user_db, post_db, etc.)

- Provision ElastiCache Redis cluster (cluster mode, 3 shards) for feed caching, session storage, rate limiting

- Create DynamoDB tables: PostLikes, PostComments, UserFollows, FeedItems, Notifications — define GSIs for all access patterns now

- Store all DB credentials, API keys in Secrets Manager. Configure IRSA so each K8s service account can only read its own secrets

- Set up Cognito User Pool — enable Google OAuth, configure JWT token expiry, create app clients for web and API

- Build GitHub Actions CI pipeline: lint → test → docker build → push to ECR on every PR merge to main

- Install ArgoCD on EKS. Create ArgoCD applications pointing to your Helm chart repo. Test with a dummy deployment

- Set up local dev environment: Docker Compose with local Postgres, Redis, and LocalStack for AWS service mocking

AuroraElastiCacheDynamoDBCognitoSecrets ManagerArgoCD

Full infra provisioned. CI pipeline pushes images to ECR. ArgoCD deploys to EKS on git push.

Phase 2 — Core microservices (weeks 3–5)

Build the user service, post service, media service, and interaction service. Wire them to the databases. Write Kubernetes manifests for each. Get a working end-to-end flow: register → login → create post with image → like it.

Weeks 3–5 4 microservices First working demo

Week 3

User service + auth flow

- Scaffold Node.js + TypeScript + Fastify project. Set up Prisma with Aurora. Define User, Follow schema with migrations

- Build endpoints: POST /register, POST /login (Cognito), GET /users/:id, PUT /users/:id (update profile), DELETE /users/:id

- Build follow system: POST /users/:id/follow, DELETE /users/:id/follow, GET /users/:id/followers (paginated), GET /users/:id/following

- Implement Cognito JWT validation middleware — verify token on every protected route, extract userId from claims

- Write Dockerfile (multi-stage build), Helm chart with Deployment, Service, HPA, ConfigMap, ServiceAccount with IRSA annotation

- Write unit tests with Jest. Integration tests against local Postgres via Docker Compose. Target 70% coverage

- Deploy to EKS dev namespace via ArgoCD. Verify with curl. Set up basic CloudWatch log group

AuroraCognitoEKSSecrets Manager

Register, login, follow/unfollow working end-to-end on EKS

Week 4

Post service + media pipeline

- Build Post service: POST /posts (create with text + optional media), GET /posts/:id, DELETE /posts/:id, GET /users/:id/posts (paginated)

- Parse hashtags on post creation — extract and store in a PostHashtags table in Aurora for search later

- Build Media service: generate S3 presigned upload URL, return it to client. Client uploads directly to S3 (never through your server)

- Write Lambda function triggered on S3 PutObject event — uses Sharp to resize image to 4 sizes (thumbnail, small, medium, large), saves back to S3 under /processed/ prefix

- Configure CloudFront distribution pointing to S3. All media URLs returned to clients use CloudFront domain, not S3 directly

- For video: S3 trigger invokes Lambda which submits a MediaConvert job to transcode to HLS. Store CloudFront HLS URL in post record once complete

- Write Helm charts for both services. Deploy to EKS. Test full flow: upload image → get CloudFront URL → create post with URL

S3LambdaCloudFrontMediaConvertAurora

Image posts work. CloudFront serves resized images. Video transcoding pipeline functional.

Week 5

Interaction service + API Gateway

- Build Interaction service using DynamoDB — PK=postId, SK=userId for likes. Enables O(1) like/unlike and "did this user like this post?" checks

- Implement like counter buffering: increment a Redis counter on like. A Lambda cron runs every 30s and batch-flushes counts to Aurora. Prevents write storms on viral posts

- Build comments: POST /posts/:id/comments, GET /posts/:id/comments (threaded, paginated), DELETE /comments/:id. Store in DynamoDB

- Implement reposts and bookmarks — DynamoDB tables with GSI on userId for "my bookmarks" and "my reposts" queries

- Set up API Gateway HTTP API as the single entry point for all microservices. Configure routes, Cognito JWT authorizer, and VPC Link to reach EKS pods

- Configure WAF on API Gateway — rate limit to 100 req/min per IP on post creation, block common injection patterns

- Build the React frontend skeleton: auth pages, profile page, post creation form with image upload. Wire to real APIs

DynamoDBElastiCacheAPI GatewayWAFCognito

Full working app: register, post, like, comment, bookmark. Frontend connected to real AWS APIs.

Phase 3 — Feed engine & notifications (weeks 6–7)

The hardest and most impressive part. Build the hybrid fan-out feed system and the real-time notification service. This is the engineering that separates this project from a basic CRUD app.

Weeks 6–7 Hardest phase Fan-out + real-time

Week 6

Hybrid fan-out feed engine

Design Redis data structure: each user's feed is a sorted set — key is feed:{userId}, score is post timestamp (Unix ms), value is postId. Capped at 800 items max per user

When a post is created, Post service publishes a PostCreated event to SNS. SNS fans out to two SQS queues: FanoutQueue (for regular users) and AnalyticsQueue

Build Fan-out Worker as a separate EKS deployment. It consumes FanoutQueue messages. For each post: check author follower count. If under 10k followers, fetch all follower IDs from DynamoDB (paginated GSI query) and ZADD the postId to each follower's Redis feed sorted set

For celebrity users (10k+ followers): skip fan-out. Store a "celebrity follows" list per user in Redis. At feed read time, merge celebrity posts from a shared celebrity:{userId} sorted set into the user's personal feed

Build Feed service GET /feed endpoint: ZREVRANGE feed:{userId} 0 19 from Redis to get top 20 postIds by score. Batch-fetch post details from Post service. Merge in celebrity posts. Return hydrated feed with cursor for pagination

Handle feed gaps: if Redis feed has fewer than 5 items (new user or cache miss), fall back to a direct Aurora query joining follows and posts ordered by created_at. Backfill Redis async

HPA on Fan-out Worker deployment based on SQS queue depth (custom metric via KEDA or CloudWatch metric adapter). Scales 1→20 pods under viral load

SQS

SNS

ElastiCache

DynamoDB

EKS HPA

Post by user A appears in all followers' feeds within 2 seconds. Celebrity posts merge correctly at read time.

Week 7

Notification service + search

Build Notification service. Subscribes to SNS topics: PostLiked, PostCommented, UserFollowed, PostReposted. On each event, write a notification row to DynamoDB with userId, type, actorId, postId, read=false, createdAt

Unread notification count: INCR notif:unread:{userId} in Redis on each new notification. Reset to 0 on GET /notifications (mark all read)

API Gateway WebSocket API for real-time in-app notifications. On connect, Lambda stores connectionId → userId mapping in DynamoDB. On new notification, Notification service calls API Gateway Management API to push to live connection

Email notifications via SES: first-time follower, weekly digest. Use SES templates. Rate-limit emails per user to avoid spam (Redis counter: email:{userId}:{date})

Build Search service using OpenSearch (or Aurora full-text search for simpler setup). Index users (username, bio) and posts (content, hashtags). Endpoints: GET /search/users?q=, GET /search/posts?q=, GET /search/hashtags?q=

Post service publishes PostCreated events consumed by Search service to index new posts in near-real-time via SQS

Wire notifications bell in React frontend. WebSocket client reconnects on disconnect. Unread count badge updates in real time

API Gateway WS

SES

DynamoDB

SNS

ElastiCache

Real-time notification bell works. Like on a post → author sees it instantly. Search returns users and posts.

Phase 4 — Frontend, observability & security (week 8)

Polish the React frontend to a real product feel. Wire up distributed tracing across all 8 services. Harden security. This is where the project goes from a tech demo to something you can proudly show.

Week 8 Frontend polish Observability

Week 8 — Part A

Frontend completion

- Home feed page: infinite scroll with React Query + cursor pagination, optimistic like/unlike updates, skeleton loading states

- Profile page: avatar, bio, post grid, followers/following counts with modal lists, follow button with instant optimistic update

- Post detail page: full post, threaded comments, repost/bookmark actions, share link

- Post composer: rich text, image drag-and-drop upload with preview, character counter, hashtag autocomplete

- Notifications page: grouped by type (likes, comments, follows), mark-all-read, real-time badge via WebSocket

- Search page: debounced search input, results tabbed by users/posts/hashtags, follow from search results

- Build React app with Vite, deploy static files to S3, serve via CloudFront. Set up Route 53 domain with SSL cert via ACM

S3CloudFrontRoute 53ACM

Full working UI on a real domain with HTTPS. Looks and feels like a real social app.

Week 8 — Part B

Observability & security hardening

- Add X-Ray SDK to all 8 services. Instrument every HTTP handler and DB call. Configure X-Ray daemon as a sidecar in each K8s pod. Verify traces show full request path across services in AWS console

- Install Prometheus + Grafana on EKS monitoring namespace via Helm. Configure ServiceMonitor for each microservice. Build Grafana dashboard: feed latency p50/p95/p99, SQS queue depth, Redis hit rate, error rate per service

- Structured logging in every service: JSON logs with traceId, userId, requestId, duration. Ship to CloudWatch Logs. Create CloudWatch metric filters for error rate alarms

- Apply Kubernetes Network Policies: each service can only talk to its own database and the services it explicitly needs. No pod-to-pod free-for-all

- Enable KMS encryption for Aurora, ElastiCache, DynamoDB, S3. Rotate Secrets Manager secrets on a schedule

- WAF rules on CloudFront: geo-blocking, rate limiting on API routes, SQL injection and XSS protection managed rules

- Run AWS Trusted Advisor and Security Hub scan. Fix all critical findings before final deployment

X-RayCloudWatchPrometheusKMSWAF

Full distributed traces. Grafana dashboards live. Security hardened and verified

Phase 5 — Load testing, production deploy & documentation (weeks 9–10)

Prove the system works under load. Deploy to production. Write architecture docs. Record a demo video. This is what turns the project into a portfolio piece that gets you hired.

Weeks 9–10 Production ready Portfolio ready

Week 9

Load testing & production hardening

- Write k6 load test scripts: simulate 500 concurrent users creating posts, fetching feeds, liking posts. Run against staging. Target: feed endpoint p95 under 200ms

- Simulate viral post: one user followed by 5000 others creates a post. Measure fan-out worker scaling via HPA. Verify all 5000 feeds updated within 30 seconds

- Tune ElastiCache connection pools, Aurora max_connections, and DynamoDB provisioned capacity based on load test results

- Implement pod disruption budgets for all services — ensure at least 1 replica always running during node drain or deploy

- Configure Aurora read replicas. Route all GET endpoints to the read replica. Only writes go to the primary

- Set up CloudWatch alarms: SQS queue depth > 10k, feed latency p95 > 500ms, error rate > 1%, ElastiCache memory > 80%

- Chaos test: manually kill a pod mid-request. Verify graceful shutdown, no 5xx to clients, ArgoCD auto-restarts it

k6CloudWatch AlarmsAurora replicasHPA

System handles 500 concurrent users. Fan-out scales automatically. No single point of failure.

Week 10

Production deployment & portfolio wrap-up

- Promote staging ArgoCD apps to production namespace. Verify all environment variables, secrets, and database connections in prod

- Configure Route 53 health checks on all API endpoints. Set up CloudWatch Synthetics canary pinging the feed API every minute

- Set up AWS Budgets alert at $50/month to avoid bill shock. Review and right-size all resources (use t3.small for low-traffic services)

- Write architecture README: system design diagram, every AWS service and why it was chosen, the fan-out design decision, tradeoffs made

- Record a 5-minute demo video: show feed updating in real time across two browser tabs, show Grafana dashboard under load, show X-Ray trace of a post creation end-to-end

- Write a detailed blog post / LinkedIn article explaining the fan-out architecture and the tradeoffs. This alone gets attention from engineers

- Push all Terraform, Helm charts, and application code to a public GitHub repo with a polished README

Route 53CloudWatch SyntheticsAWS BudgetsArgoCD

Live on a real domain. Public GitHub repo. Demo video recorded. Ready for interviews.